## Overview
Mini ISO 27001 Gap Assessment Project Pack
Fictional case study for a cloud-native SaaS company (NorthstarHR)
Purpose: demonstrate ISO 27001:2022 gap assessment, risk prioritization, and remediation planning.
Project Summary |  | Assessment Metrics | Navigation
Client profile | NorthstarHR is a fictional 25-person HR SaaS startup handling employee PII. | Total controls | Control Matrix
Assessment scope | Core SaaS app, AWS production, Microsoft 365, endpoint security, vendor management, backups, and incident response. | Implemented | Findings Register
Assessment method | Review selected ISO clauses and 24 Annex A controls using a simple maturity score: 0 absent, 1 partial, 2 implemented. | Partial | Roadmap
|  | Not implemented | Questionnaire
Control Status Distribution
Implemented |  | High-risk findings
Partial
Not Implemented
Top Deliverables Included
- Assessment workbook with control matrix, findings register, roadmap, and questionnaire.
- Portfolio-ready report summarizing scope, method, findings, and showcase guidance.
- Risk-prioritized sample gaps suitable for LinkedIn, GitHub, or personal portfolio use.

## Control Matrix
Control Matrix
Scoring: 0 absent, 1 partial, 2 implemented
Domain | Control Ref | Control Title | Objective | Current State | Evidence / Assumption | Status | Score | Priority | Recommendation
Clause | 4.1 | Context of the organization | Define internal/external issues | Ad hoc business context, no formal ISMS scoping memo | Leadership understands business risks but no documented context analysis | Partial | 1 | Medium | Create ISMS context statement and define interested parties.
Clause | 5.1 | Leadership and commitment | Show management support | Security ownership exists but no formal steering cadence | CTO sponsors security work informally | Partial | 1 | High | Establish monthly security governance review with action tracking.
Clause | 6.1 | Risk assessment process | Use repeatable risk method | Informal risk reviews only during incidents | No approved risk methodology or criteria | Not Implemented | 0 | High | Create risk methodology with likelihood, impact, and treatment rules.
Clause | 6.2 | Security objectives | Define measurable objectives | Security goals are implied, not measured | No KPI/KRI set for ISMS | Not Implemented | 0 | Medium | Set quarterly objectives for patching, phishing, backups, and access reviews.
Clause | 7.2 | Competence | Ensure staff competence | Security training exists only for IT team | No role-based competence matrix | Partial | 1 | Medium | Build role-based training plan for engineers, admins, and managers.
Clause | 7.5 | Documented information | Control security documents | Policies scattered across docs and wiki | No document owner or review cycle | Partial | 1 | High | Create policy library with owners, versioning, and annual review dates.
Annex A | A.5.9 | Inventory of information and assets | Track critical assets | Cloud assets partly tracked; endpoints tracked in EDR | No unified inventory | Partial | 1 | High | Create centralized asset register for systems, data stores, devices, and owners.
Annex A | A.5.15 | Access control | Control logical access | SSO used for some apps but access reviews are inconsistent | M365 and AWS have separate practices | Partial | 1 | High | Document JML process and quarterly access recertification.
Annex A | A.5.16 | Identity management | Manage identities lifecycle | Provisioning is ticket-based and manual | No evidence of periodic entitlement validation | Partial | 1 | High | Define identity lifecycle workflows and evidence retention.
Annex A | A.5.17 | Authentication information | Protect credentials | MFA enabled for admins but not all users | Password standard exists only in onboarding checklist | Partial | 1 | High | Mandate MFA for workforce and privileged accounts.
Annex A | A.5.19 | Supplier relationships | Manage supplier security | Vendors are reviewed informally by engineering | No standard due diligence checklist | Not Implemented | 0 | High | Create vendor security review questionnaire and tiering model.
Annex A | A.5.23 | Information security for cloud services | Control cloud service risks | AWS used extensively with baseline controls | No documented cloud security standard | Partial | 1 | High | Create cloud baseline covering logging, IAM, encryption, and backups.
Annex A | A.5.24 | Incident management planning and preparation | Prepare for incidents | IR steps known by security team only | No approved playbooks or tabletop evidence | Not Implemented | 0 | High | Publish incident response plan and run tabletop exercise.
Annex A | A.5.30 | ICT readiness for business continuity | Prepare technology continuity | Backups exist but restore tests are inconsistent | No formal RTO/RPO mapping | Partial | 1 | High | Define critical service RTO/RPO and test restoration quarterly.
Annex A | A.7.2 | Physical entry controls | Restrict office access | Office access handled by building management | No retained access review evidence | Partial | 1 | Low | Document building access expectations and termination checks.
Annex A | A.7.7 | Clear desk and clear screen | Protect exposed information | No written standard | Remote-first environment reduces exposure but laptops are used in co-working spaces | Not Implemented | 0 | Low | Add clear-screen expectations to acceptable use and awareness training.
Annex A | A.8.1 | User endpoint devices | Secure endpoints | EDR present and patching partly managed | No formal endpoint baseline | Partial | 1 | High | Create endpoint baseline for encryption, patching, EDR, screen lock, and admin rights.
Annex A | A.8.2 | Privileged access rights | Restrict privileged access | Admins are limited but not formally reviewed | Privileged role list not documented | Partial | 1 | High | Define privileged roles, approvals, and quarterly reviews.
Annex A | A.8.5 | Secure authentication | Use secure auth methods | SSO plus MFA for some systems | Legacy systems still use password only | Partial | 1 | Medium | Expand SSO/MFA coverage and remove legacy standalone credentials.
Annex A | A.8.9 | Configuration management | Control secure configurations | Cloud configs mostly manual | No approved hardening baseline | Not Implemented | 0 | High | Create secure build standards and baseline validation.
Annex A | A.8.12 | Data leakage prevention | Prevent unauthorized disclosure | No DLP tooling or classification workflow | PII handling relies on employee judgment | Not Implemented | 0 | High | Start with data classification and lightweight DLP for email/storage.
Annex A | A.8.15 | Logging | Record security events | AWS and M365 logging enabled in parts | No unified logging standard or retention policy | Partial | 1 | High | Define logging baseline, retention, and monitoring use cases.
Annex A | A.8.16 | Monitoring activities | Monitor anomalies | Alerting exists for endpoints, limited cloud detections | Coverage gaps across SaaS and admin actions | Partial | 1 | Medium | Map top attack paths to detection rules and owner review cadence.
Annex A | A.8.23 | Web filtering | Reduce malicious web access | Browser controls vary by team | No centralized policy | Not Implemented | 0 | Low | Enable DNS/web filtering for managed devices.

## Findings Register
Findings Register
Eight portfolio-ready findings derived from the control matrix.
ID | Category | Finding | Risk Statement | Impact | Likelihood | Impact Rating | Risk | Owner | Recommended Action
F-01 | Governance | No formal risk assessment methodology | Security decisions may be inconsistent and hard to defend during audits. | High | High | High | High | Security Lead | Approve risk method and maintain a treatment register.
F-02 | Documentation | Policy set lacks owner and review cadence | Policies may become outdated and fail to guide operations. | Medium | High | Medium | High | Compliance Owner | Publish policy library with annual review dates.
F-03 | Asset Mgmt | No centralized asset inventory | Critical systems and data stores may be missed during risk reviews or incidents. | High | Medium | High | High | IT Operations | Build single source of truth for systems, devices, and data assets.
F-04 | Access Control | Access reviews are inconsistent | Excessive access may remain after role changes or offboarding. | High | High | High | High | IT / HR | Run quarterly recertification and document joiner-mover-leaver workflow.
F-05 | Supplier Risk | Vendor due diligence is informal | High-risk suppliers may process data without appropriate security review. | High | Medium | High | High | Procurement | Create vendor tiering and review checklist before onboarding.
F-06 | Incident Response | No approved IR plan or tabletop exercise | Major incidents may be escalated slowly and without clear roles. | High | Medium | High | High | Security Lead | Publish playbooks and run at least one tabletop.
F-07 | Resilience | Backups are not restore-tested regularly | Recovery may fail during ransomware or cloud outages. | High | Medium | High | High | Platform Team | Set RTO/RPO and evidence quarterly restore tests.
F-08 | Monitoring | Logging and detection coverage is fragmented | Threat activity may go undetected across cloud and SaaS admin actions. | Medium | Medium | Medium | Medium | SOC / Security Ops | Define logging standard and expand detections by threat scenario.

## Roadmap
90-Day Remediation Roadmap
Prioritized plan for quick wins and audit-readiness improvement.
Phase | Timeline | Workstream | Action | Owner | Effort | Dependency
Phase 1 | Days 1-30 | Governance | Approve ISMS scope, risk method, policy owners, and review calendar. | Leadership / Security | Medium | Executive sponsor
Phase 1 | Days 1-30 | Access | Define JML workflow, privileged roles, and quarterly access review process. | IT / HR | Medium | Identity data
Phase 1 | Days 1-30 | Incident Response | Draft IR plan, communications matrix, and ransomware playbook. | Security | Medium | Management review
Phase 2 | Days 31-60 | Asset Management | Build asset register for systems, data stores, devices, and vendors. | IT / Security | High | CMDB or spreadsheet
Phase 2 | Days 31-60 | Cloud Security | Publish AWS baseline for IAM, logging, encryption, backups, and configuration review. | Cloud Team | High | Architecture input
Phase 2 | Days 31-60 | Supplier Risk | Create vendor tiering and due diligence checklist. | Procurement / Security | Medium | Legal templates
Phase 3 | Days 61-90 | Monitoring | Define logging standard and add prioritized detection use cases. | Security Ops | High | Log sources enabled
Phase 3 | Days 61-90 | Resilience | Run backup restore test and tabletop exercise; capture lessons learned. | Platform / Security | Medium | Approved playbooks

## Questionnaire
Stakeholder Interview Questionnaire
Use these prompts during a mini assessment workshop.
Area | Question | Suggested Evidence | Primary Stakeholder | Priority
Governance | How is information security risk assessed, approved, and tracked? | Risk register, risk methodology, meeting notes | Security Lead / CTO | High
Policies | Which security policies exist, who owns them, and how often are they reviewed? | Policy library, approval dates | Compliance Owner | High
Assets | Do you maintain an inventory of systems, endpoints, data stores, and critical SaaS apps? | Asset register, CMDB, cloud inventory exports | IT Operations | High
Access | How are users provisioned, deprovisioned, and access-reviewed after role changes? | HR workflow, IAM screenshots, review evidence | IT / HR | High
Suppliers | How are vendors assessed before they process company or customer data? | Vendor checklist, contracts, security reviews | Procurement | High
Incident Response | What happens during a security incident, and when was the last exercise? | IR plan, playbooks, tabletop notes | Security Team | High
Backups | Which systems are backed up and when was recovery last tested? | Backup schedule, restore results | Platform Team | High
Logging | Which logs are retained, monitored, and reviewed? | SIEM configs, retention settings, alert runbooks | Security Ops | Medium
Endpoints | What controls exist for encryption, patching, EDR, and admin rights? | MDM/EDR settings, patch reports | IT Operations | Medium
Training | How do role-based security awareness and admin training work? | Training matrix, completion reports | HR / Security | Medium